## Proposal
Milestone | Deliverable | Tasks | Timeline
"Expanding the vortex FN results to white light to enable the comparative study between the vortex FN and the dual-aperture FN." | "We will couple the coherent He-Ne laser light into the single-mode fiber using the back-propagation method as mentioned in the risk management plan. The target coupling efficiency is >50%." | 1. Install vortex waveplate and ensure it operates as expected (nulling at the center, couples light off-axis). | 7/22 - 10/22
2. Perform backpropagation and optimize coupling with vortex waveplate installed.
| AO coupling: "We will apply the EFC algorithm to reduce the wavefront RMS error to 12 nm" | 1. Develop a pipeline to communicate with DM in real-time.
2. Implement EFC algorithm.
3. Optimize wavefront correction.
| "We will conduct the white-light (10% bandwidth) experiment and apply different Zernike modes using the DM to confirm the sensitivity of starlight suppression of the vortex FN to low-order aberrations." | 1. Make a library of Zernike modes for the DM.
2. Set-up backend for measuring starlight suppresion.
3. Run the experiment.
| "We will repeat the test on the vortex FN at the stage of near-infrared coherent and incoherent light for the comparative study between the two FN concepts." | 1. Integrate near-IR source into setup.
2. Run the Zernike modes experiment.
"Demonstrating the dual-aperture FN technique using coherent light in optical wavelengths." | "We will align and minimize wavefront errors (<20 nm) for Path 1 and 2 using EFC." | 1. Expand EFC algorithm to account for two paths. | 10/22 - 3/23
2. Test and optimize wavefront error.
3. Integrate a second DM (one for each path) if wavefront error is not within threshhold.
| "We will build a fiber-tracking system at the focal plane to assist the fiber coupling (target coupling efficiency: 10%)." | 1. Install beamsplitter before collimated light feeds into fiber injection optic.
2. Reimage secondary path onto a CCD.
3. Implement fiber tracking to maximize coupling.
| "We will apply different Zernike modes using the DM to confirm the sensitivity of starlight suppression of the dual-aperture FN to low-order aberrations." | 1. Run the experiment.
"Designing and manufacturing a beam-shaping device to increase the fiber coupling efficiency from 10% to 30%." | "We will conduct a trade-off study between mode matching and focal-ratio matching to determine an optimal PSF aspect ratio for fiber coupling." | 1. Model mode-matching. | 3/23 - 7/23
2. Model focal-ratio matching. Compare and determine optimal PSF aspect ratio.
| "We will study the dual-cylindrical lens design that results in the optimal PSF aspect ratio." | 1. Model lens designs.
| "We will design and manufacture a PIAA optics that shapes the interferometer PSF into a Gaussian beam." | 1. Zhu Li, do the thing.
"Developing a fringe tracking system to demonstrate the white-light performance in visible light." | "We will use the EFC algorithm to measure and correct for wavefront errors." | 1. Done in previous steps. | 7/23 - 1/24
| Linear stage: "We will automate the control of a linear stage for Path 2 in order find the location with zero optical path difference (OPD) where there is the maximum fringe visibility." | 1. Install linear stage for CCR.
| "We will add a fringe tracking system by splitting light at the current vortex plane location in order to achieve real-time fringe tracking." | 1. Done in previous steps.
| "We will integrate the linear stage controlling system and the fringe tracking system to feed the white light into the single-mode fiber." | 1. Optimize coupling.
| "We will measure how spectral bandwidth and the integrated system affects the performance of the dual-aperture FN." | 1. Integrate input source with tunable spectral bandwidth.
2. Run Zernike modes experiment with different spectral bandwidths.
"Demonstrating the near-infrared spectroscopic performance." | "We will test the super continuum, hydrogen cyanide, and the near-infrared spectrometer in a separate system." |  | 1/24 - 6/24
"We will replace the camera in the fringe tracking system with a near-infrared camera and realize the fringe tracking in near-infrared."
"We will demonstrate the dual-aperture FN in near infrared with a single-mode fiber."
"We will produce the hydrogen cyanide spectrum with the integrated dual-aperture FN spectroscopic system."
"Conducting the design reference study for a new LBTI instrument using the dual-aperture FN technique." | "We will update target list for the two science cases." |  | 7/24 - 6/25
"We will conduct simulations to determine the system requirements (e.g., image quality, wavelength coverage, spectral resolution, total throughput, field of view)."
"We will complete a traceability matrix to link science cases to system requirements and perform trade study."
"We will have conceptual designs for the front-end module and the high-resolution spectrograph, and estimate the cost and time scale of the instrument development."